## Test Scenarios
Project Name | bdshop
Reference Document | N/A
Created By | Nowme Zaman
Creation Date | 15-02-204
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_01 |  | Validate the URL in different browsers | P0 | 1
TS_02 |  | Validate the "Register" functionality | P1 | 63
TS_03 |  | Validate the "Login" functionality | P0 | 27

## test_cases
Product Name |  | BD Shop | TC Start Date | 2024-02-11 | TC Execution Start Date | 2024-02-14 |  |  |  |  | TEST CASE
Module Name |  | Sign Up, Sign In, Forgot Password | TC End Date | 2024-02-11 | TC Execution End Date | 2024-02-14 |  |  |  |  | PASS | 73
Epic |  |  | Test Case Developed By | Nowme Zaman | Browser (tested) | Yes |  |  |  |  | FAIL | 19
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | No |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | 92
#SL | Module | Type of Testing | Features | Test Cases Descripton | Expected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing |  | Verify the site runs in different browsers | Should run in different browsers | Found as per expectation | Chrome Internet Explorer Mozilla Firefox Microsoft Edge | 1. Goto different browsers 2. Search 'BD Shop' 3. Goto the website |  |  | Passed
2 | User Management | UI Testing | Sign Up | Verify the style, font and color | Should be as per requirements | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check the font, text color and style |  |  | Passed
3 |  |  |  | Verify the site is free of spelling and grammatical errors | Should be as per requirements | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check spelling and grammatical errors fom the website |  |  | Passed
4 |  |  |  | Verify responsiveness of the sign up form | Should be fully responsive | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on register button 3. Check responsiveness of the page |  |  | Passed
5 |  |  |  | Verify the hover effect on all fields | Should be as per requirements | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Hover over every fields |  |  | Passed
6 |  |  |  | Verify the presence of checkbox beside 'remember me' | Should be as per requirements | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Verify the presence of checkbox |  |  | Passed
7 |  |  |  | Verify captcha is marked with red asterisk | Should be as per requirements | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on register button 3.Check captcha is marked with a red asterisk |  |  | Passed
8 |  |  |  | Verify the alignment of the fields | Should be as per requirements | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check the alignment of the fields |  |  | Passed
9 |  |  |  | Verify all mandatory fields are marked with red asterisk | All mandatory fields should be marked with a red asterisk | Red asterisk mark is missing for Phone number field | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check phone number field | Phone number field missing red asterisk |  | Failed
10 |  |  |  | Verify all fields has label tag | All fields should have label tag | Phone number field has no label tag | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check phone number field | phone number missing label |  | Failed
11 |  |  |  | Verify all input fields has placeholder attribute | Should be as per requirements | Not found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Verify the presence of placeholder attribute for all fields | fields are missing placeholder attribute |  | Failed
12 |  |  |  | Verify the presence of checkbox beside 'Sign up for Newsletter' | Should be as per requirements | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Verify the presence of checkbox beside 'Sign up for newsletter' |  |  | Passed
13 |  | Functional Testing |  | Verify sign up functionality by keeping all mandatory fields blank | Should not allow user to register and pop an error message | found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3.Keep all mandatory fields blank |  |  | Passed
14 |  |  |  | Verify alert messages pop up for all mandatory fields | Should pop an error message | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Input AbbCCdd and uuXXggDD in firstname and lastname field |  |  | Passed
15 |  |  |  | Verify first name and last name fields by keeping them empty | Should not allow user to register and pop an error message | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Keep first name and last name fields empty |  |  | Passed
16 |  |  |  | Verify first name and last name fields are case insensitive | Fields should be case insensitive | found as per expectation | asdbbss Sfghjjj | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Input data in small letters for first name and last name Fields |  |  | Passed
17 |  |  |  | Verify first name and last name fields with blank spaces at beginning and end of fields | Should not accept blank spaces at the beginning and end of fields | Not found as per expectation | sfafas sdasdasd | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Add spaces at the beginning and end of first name and last name fields | Blank spaces at the beginning and end of fields |  | Failed
18 |  |  |  | Verify first name and last name fields with alphabets | Should accept alphabets | found as per expectation | James rosewood | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Keep blank spaces in each field and checking repeatedly |  |  | Passed
19 |  |  |  | Verify first name and last name fields with special characters | Should not accept special characters | Not found as per expectation | !@#$%&*() ,./?';"{}[]\_= | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter special characters in firstname and lastname fields | Special character error |  | Failed
20 |  |  |  | Verify first name and last name fields with numbers | Should not accept numbers | Not found as per expectation | 575745757 343434 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter numbers in firstname and lastname fields | Numbers error |  | Failed
21 |  |  |  | Verify first name and last name fields with decimal numbers | Should not accept decimal numbers | Not found as per expectation | 567.6544.554 3467.8900 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter decimal numbers in firstname and lastname fields | Decimal numbers in input fields |  | Failed
22 |  |  |  | Verify first name and last name fields with comma between alphabets | Should not accept comma between alphbets | Not Found as per expectation | ram,isa araf,at | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter comma between alphabets in firstname and lastname fields | Comma between alphabets in input fields |  | Failed
23 |  |  |  | Verify first name and last name fields with space between alphabets | Should accept the provided input | Found as expected | John Diaz Ashey Brown | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter space between alphabets in firstname and lastname fields |  |  | Passed
24 |  |  |  | Verify first name and last name fields with alphanumeric characters | Should not accept the provided input | Not found as per expectation | Ash@$* 0Brown12 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter alphanumeric characters in firstname and lastname fields | alphanumeric characters in input fields |  | Failed
25 |  |  |  | Verify checkbox for Remember Me | Should function successfully | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Select the checkbox of Remember me |  |  | Passed
26 |  |  |  | Verify checkbox for newsletter | Should function successfully | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Select the checkbox of newsletter |  |  | Passed
27 |  |  |  | Verify email field by keeping it blank | Error message will pop up | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Keep the email field blank |  |  | Passed
28 |  |  |  | Verify email field with invalid format | Should not accept the provided input and an error message will pop up | Found as expected | adsdadd@dast | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Fill the email address field with invalid format |  |  | Passed
29 |  |  |  | Verify email field with valid format | Should accept the provided input | Found as expected | nowmezaman@gmail.com | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Fill the email address field with valid format |  |  | Passed
30 |  |  |  | Verify email address is unique and can be used for one account | Should not allow same email address to create more than one account | Found as expected | nowmezaman@gmail.com | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Register more than one account with same email address |  |  | Passed
31 |  |  |  | Verify password and confirm password fields are masked | Should be masked | Found as expected | Dell1345 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter combinations of characters and number in password and confirm password fields |  |  | Passed
32 |  |  |  | Verify password and confirm password fields with different data | Should not allow user to register and display an error message | Found as expected | password: daisy2345 Confirm-password: Daisy@1111 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter weak password length in password and confirm password |  |  | Passed
33 |  |  |  | Verify password and confirm password fields with same data | Should allow user to register | Found as expected | password: Daisy13 Confirm password: Daisy13 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter same data in password and confirm password fields |  |  | Passed
34 |  |  |  | Alert message pops up when password and confirm password fields' data are different | Should not allow user to register and display an error message | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter different data for password and confirm password fields |  |  | Passed
35 |  |  |  | Verify weak password strength | Should allow user to register | Found as expected | bell13 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter weak password length in password and confirm password |  |  | Passed
36 |  |  |  | Verify medium password strength | Should allow user to register | Found as expected | Zaman123 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter medium password length in password and confirm password fields |  |  | Passed
37 |  |  |  | Verify strong password strength | Should allow user to register | Found as expected | Zaman!12345 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter strong password length in password and confirm password fields |  |  | Passed
38 |  |  |  | Verify 'Sign up for Newsletter' is not enabled by default | Should be disabled by default | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check sign up for newsletter is disabled |  |  | Passed
39 |  |  |  | Verify 'Remember Me' is not enabled by default | Remember Me' option should be disabled | Not found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check the 'Remember Me' option | remember me option is enabled |  | Failed
40 |  |  |  | Verify by enabling 'Remember Me' checkbox and visit the site | Should remember credentials | Found as expected | Firstname: Robbert Lastname: smith Email: nowmezaman@gmail.com Password: Nz1234 Confirm Password: Nz1234 Remember Me: Select checkbox | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Fill all the fields with valid credentials 4. Enable 'Remember Me' 5. Visit the site again |  |  | Passed
41 |  |  |  | Verify by not enabling 'Remember Me' checkbox and visit the site | Should not remember credentials | Found as expected | Firstname: Robbert Lastname: smith Email: nowmezaman@gmail.com Password: Nz1234 Confirm Password: Nz1234 Remember Me: Unselect checkbox | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Fill all the fields with valid credentials 4. Disable 'Remember Me' 5. Visit the site again |  |  | Passed
42 |  |  |  | Verify phone number field by keeping it blank | Should not allow user to register and alert message pops up | Not found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check phone number field by keeping it empty | phone number field is blank |  | Failed
43 |  |  |  | Verify phone number with alphabets | Should not accept the provided input | Found as expected | asdsadfdgd | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check phone number field with alphabets |  |  | Passed
44 |  |  |  | Verify phone number with special characters | Should not accept the provided input | Found as expected | dsd!@(*&% | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check phone number field with special characters |  |  | Passed
45 |  |  |  | Verify phone number with comma between numbers | Should not accept the provided input | Not Found as per expectation | 23,3443,33 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check phone number field with comma between numbers | phone number has comma between numbers |  | Failed
46 |  |  |  | Verify phone number with label | Input field should have label | Not found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check phone number fields label | Phone number field with no label |  | Failed
47 |  |  |  | Verify phone number with red asterisk mark | Should have red asterisk mark | Not found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check phone number field marked with red asterisk | Phone number field missing red asterisk mark |  | Failed
48 |  |  |  | Verify phone number with space between numbers | Should not accept the provided input | Not Found as per expectation | 44 34 343 43 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. check phone field with space between numbers | phone number with space between numbers |  | Failed
49 |  |  |  | Verify phone number with numbers | Should accept the provided input | Found as expected | 231231231 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check phone number field with numbers |  |  | Passed
50 |  |  |  | Verify captcha with empty field | Should not allow user to register and display an error message | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Fill all the fields with valid credentials 4. Keep captcha field blank |  |  | Passed
51 |  |  |  | Verify captcha with invalid data | Should not accept the provided input | Found as expected | gh2U | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Fill all the fields with valid credentials 4. check captcha field with invalid input |  |  | Passed
52 |  |  |  | Verify captcha with valid data | Should allow user to register | Found as expected | 5B311 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Fill all the fields with valid credentials 4. check captcha field with valid input |  |  | Passed
53 |  |  |  | Verify captcha is case sensitive | Should be case sensitive | Found as expected | ChI9w | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Fill all the fields with valid credentials 4. Fill the captcha with upper and lower case alphabets |  |  | Passed
54 |  |  |  | Verify captcha reload button | Should generate new captcha | Found as expected | m5tHa | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. check captcha reload button |  |  | Passed
55 |  |  |  | Verify new captcha is generated when page loads | Should generate new captcha | Found as expected | 4BgtJ | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Reload the site again 4. New captcha will be generated |  |  | Passed
56 |  |  |  | Verify new captcha is generated after adding wrong captcha | Should generate new captcha | Found as expected | A2eB | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Fill all the fields with valid credentials 4. Fill captcha field with invalid input |  |  | Passed
57 |  |  |  | Verify registration button with invalid email address | Should not allow user to register and display an error message | Found as expected | Firstname: Robbert Lastname: Smith Email: robbert@nbvc.com Password: Anz!123 Confirm Password: Anz!123 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Fill email fields with invalid email address 4. Click on 'Create an account' button |  |  | Passed
58 |  |  |  | Verify registration button with valid credentials | Should allow user to register | Found as expected | Firstname: Robbert Lastname: smith Email: nowmezaman@gmail.com Password: Nz1234 Confirm Password: Nz1234 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Fill all the fields with valid credentials 4. Click on 'Create an account' button |  |  | Passed
59 |  |  |  | Verify confirmation mail is sent to the registered email | Should sent confirmation mail successfully | Not found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Fill all the fields with valid credentials 4. Click on 'Create an account' button 5. Check mail to confirm account | Confirmation mail was not sent |  | Failed
60 |  |  |  | Verify sign up functionality with facebook | Should allow user to register | Found as expected | Click on 'Sign in with Facebook' | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Click on 'Sign in with Facebook' |  |  | Passed
61 |  |  |  | Verify sign up functionality with google | Should allow user to register | Found as expected | Click on 'Sign in with Google' | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Click on 'Sign in with Google' |  |  | Passed
62 |  | Usability Testing |  | Verify copy paste functionality in every fields | Should copy and paste text in every fields | Functioning successfully | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Copy paste text in every field |  |  | Passed
63 |  |  |  | Verify tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter tab in every field |  |  | Passed
64 |  |  |  | Verify the enter button functionality | Should switch to another field | Functioning successfully | Input Enter in every field | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Press enter in every field |  |  | Passed
65 |  | UI Testing | Sign In | Verify the style, font and color | Should be as per requirements | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Check the font, text color and style |  |  | Passed
66 |  |  |  | Verify the alignment of the Fields | Should be as per requirements | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Check the alignment of the fields |  |  | Passed
67 |  |  |  | Verify the checking of spelling and grammatical errors | Should be as per requirements | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Check spelling and grammatical errors |  |  | Passed
68 |  |  |  | Verify the hover effect on all fields | Should be as per requirements | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Check hover effects on all fields |  |  | Passed
69 |  |  |  | Verify responsiveness of the login form | Should be fully responsive | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Check responsiveness of the page |  |  | Passed
70 |  |  |  | Verifying mandatory fields are marked with red asterisk | All mandatory fields should be marked with a red asterisk | Not Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Check all mandatory fields | Mandatory fields missing red asterisk |  | Failed
71 |  |  |  | Verify the presence of checkbox beside 'Remember me' | Should be as per requirements | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3.verify the presence of checkbox beside 'Remember Me' |  |  | Passed
72 |  |  |  | Verify all input fields has placeholder attribute | Should be as per requirements | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Verify the presence of placeholder attribute for all fields |  |  | Passed
73 |  |  |  | Verify the presence of 'What's This?' beside 'Remember Me' field | Should be as per requirements | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3.Check 'What's this?' option beside 'Remember me' field |  |  | Passed
74 |  | Functional Testing |  | Verify email and password fields by keeping them blank | Should not allow user to login and display an error message | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Keep mandatory fields blank |  |  | Passed
75 |  |  |  | Verify alert messages pop up for all mandatory fields | Should display error messages for all fields | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Keep mandatory fields blank and enter login button |  |  | Passed
76 |  |  |  | Verify email field with invalid id | Should not allow user to login and display an error message | Found as expected | email: sdfsf@gmail.cm | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Login with invalid email id |  |  | Passed
77 |  |  |  | Verify email field with valid email id | Should allow user to login | Found as expected | email: nowmezaman@gmail.com | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Login with valid email id |  |  | Passed
78 |  |  |  | Verify the password field is masked | Password field should be masked | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Enter values in password field and check if it is masked |  |  | Passed
79 |  |  |  | Verify password field with valid data | Should allow user to login | Found as expected | Anz!1234 | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Enter valid credentials in password and email field to login |  |  | Passed
80 |  |  |  | Verify password field with invalid data | Should not allow user to login and display an error message | Found as expected | anz123 | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Enter wrong credentials in password field to login |  |  | Passed
81 |  |  |  | Verify by selecting 'Remember Me' checkbox | Should remember credentials | Found as expected | Email: nowmezaman@gmail.com password: Anz!13 Remember Me: select checkbox | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. login with valid credentials and select remember me checkbox |  |  | Passed
82 |  |  |  | Verify by not selecting 'Remember Me' checkbox | Should not remember credentials | Found as expected | Email: nowmezaman@gmail.com password: Anz!13 Remember Me: unselect checkbox | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. login with valid credentials and unselect remember me checkbox |  |  | Passed
83 |  |  |  | Verify sign in functionality with google | Should allow user to login | Found as expected | Click on 'Sign in with google' | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Click on 'login with Google' button |  |  | Passed
84 |  |  |  | Verify sign in functionality with facebook | Should allow user to login | Found as expected | Click on 'Sign in with facebook' | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Click on 'login with facebook' button |  |  | Passed
85 |  |  |  | Verify 'Forgot Password' functionality | Should redirect user to new web page to Change password | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Click on 'Forgot Password' button |  |  | Passed
86 |  |  |  | Verify by selecting 'Forgot password' multiple times | Account should be temporarily restricted and a message should be displayed | Found as expected | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Click on 'Forgot Password' button multiple times |  |  | Passed
87 |  |  |  | Verify the functionality of 'Login' button with invalid credentials | Should not allow user to login and display error messages | Found as expected | Email: ffsafsa@gmail.com password: aanz!13 | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Login with valid credentials |  |  | Passed
|  |  |  | Verify click here link to resend confirmation mail | Should resend confirmation mail successfully | Not found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Enter valid credentials to login 4. Click on 'click here' link to get confirmation mail | resend confirmation mail link not working |  | Failed
88 |  |  |  | Verify the functionality of 'Login' button with valid credentials | Should allow user to login | Not found as per expectation | Email: nowmezaman@gmail.com password: Anz!123 | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Login with valid credentials | Account is not verified |  | Failed | Account needs to be verified before login
89 |  | Usability Testing |  | Verify copy paste functionality in every fields | Should copy and paste text in every fields | Functioning successfully | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Copy paste text in every fields |  |  | Passed
90 |  |  |  | Verify tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Enter tab in every field |  |  | Passed
91 |  |  |  | Verify the enter button functionality | Should switch to another field | Functioning successfully | Input Enter in every field | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Press enter in every field |  |  | Passed
|  |  | Improvement Scopes | Place 'What's this?' below sign up for newsletter
Should use 'forgot password?' instead of 'forgot?'
Place 'forgot password?' below password field
Place 'What's this?' below sign up for newsletter
Maximum length for password should be defined
Country code should be added for phone number
length of phone number should be defined
Place 'Show password' option for password and confirm password fields in register page
Phone number field should be mandatory
Placeholder attribute should be added for all fields
Negative test

## test_summary_report
Test Case Report | [6 empty] | Result :
Project Name | bdshop
Module Name | User Management |  |  |  |  | Total No. | Status
Feature Name | Sign in, Sign out and Forgot password
Test Case Version | 1 |  |  |  |  | 73 | PASS
Written By | Nowme Zaman |  |  |  |  | 19 | FAIL
Executed By | Nowme Zaman |  |  |  |  | 0 | Not Executed | New Features:- | Testing Scope:- | Testing Environment :Google Chrome Browser
Reviewed By | [5 empty] | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 73 | 19 | 0 | 0 | 92
Grand Total | 73 | 19 | 0 | 0 | 92
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting
# SL 01 | # SL 02 | # SL 03 | # SL 04 | # SL 05 | # SL 06 | # SL 07 | # SL 08
Issue: Phone number field missing red asterisk mark | Issue: Phone number field has no label tag | Issue: All input fields has no placeholder attribute | Issue: First name and last name fields accept blank spaces at the beginning and end of fields | Issue: First name and last name fields accept special characters | Issue: First name and last name fields accept numbers | Issue: First name and last name fields has decimal numbers | Issue: First name and last name fields accept comma between alphabets
Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps:
1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check phone number field | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check phone number field | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check placeholder attribute for all fields | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Add spaces at the beginning and end of first name and last name fields | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter special characters in fields | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter numbers in input fields | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter decimal number in first name and last name fields | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter comma between alphabets in first name and last name fields
Env: Production | Env: Production | Env: Production | Env: Production | Env: Production | Env: Production | Env: Production | Env: Production
Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up
Severity: P | Severity: P1 | Severity: P5 | Severity: P4 | Severity: P4 | Severity: P4 | Severity: P3 | Severity: P3
Screenshot: Phone number field missing red asterisk | Screenshot: phone number missing label | Screenshot: fields are missing placeholder attribute | Screenshot: Blank spaces at the beginning and end of fields | Screenshot: Special character error | Screenshot: Numbers error | Screenshot: Decimal numbers in input fields | Screenshot: Comma between alphabets in input fields
Expected: Mandatory fields should be marked with red asterisk | Expected: All Fields should have label tag | Expected: All input fields should have placeholder attribute | Expected: Verify first name and last name fields with blank spaces at beginning and end of fields | Expected: Input fields should not accept special characters | Expected: First name and last name fields should not accept numbers | Expected: First name and last name fields should not accept decimal numbers | Expected: Should not accept alphabets between firstname and last name fields
Responsible QA: Nowme Zaman | Responsible QA: Nowme Zaman | Responsible QA: Nowme Zaman | Responsible QA: Nowme Zaman | Responsible QA: Nowme Zaman | Responsible QA: Nowme Zaman | Responsible QA: Nowme Zaman | Responsible QA: Nowme Zaman
Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting
# SL 09 | # SL 10 | # SL 11 | # SL 12 | # SL 13 | # SL 14 | # SL 15 | # SL 16
Issue: First name and last name fields has alphanumeric characters | Issue: 'Remember Me' checkbox is enabled by default | Issue: Phone number field was kept blank | Issue: Phone number field accept comma between numbers | Issue: Phone number field has no label tag | Issue: Phone number field missing red asterisk mark | Issue: Phone number field has space between numbers | Issue: Confirmation mail was not sent to the registered email address for verification
Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps: | Reproducing Steps:
1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter alphanumeric characters in firstname and lastname fields | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check the 'Remember Me' option | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check phone number field by keeping it empty | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Enter comma between numbers in phone field | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check phone number fields label | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Check phone number field | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. check phone field with space between numbers | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button 3. Fill all the fields with valid credentials 4. Click on 'Create an account' button 5. Check mail to confirm account
Env: Production | Env: Production | Env: Production | Env: Production | Env: Production | Env: Production | Env: Production | Env: Production
Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up
Severity: P3 | Severity: P2 | Severity: P3 | Severity: P3 | Severity: P4 | Severity: P1 | Severity: P1 | Severity: P0
Screenshot: alphanumeric characters in input fields | Screenshot: remember me option is enabled | Screenshot: phone number field is blank | Screenshot: phone number has comma between numbers | Screenshot: Phone number field with no label | Screenshot: Phone number field missing red asterisk mark | Screenshot: phone number with space between numbers | Screenshot: Confirmation mail was not sent
Expected: First name and last name fields should not accept alphanumeric characters | Expected: 'Remember Me' checkbox Should not be enabled by default | Expected: Phone number field should be mandatory | Expected: Phone number field should not accept comma between numbers | Expected: Phone number field should have label tag | Expected: Mandatory fields should be marked with red asterisk | Expected: Phone number Field should not accept space between numbers | Expected: Should sent confirmation mail successfully
Responsible QA: Nowme Zaman | Responsible QA: Nowme Zaman | Responsible QA: Nowme Zaman | Responsible QA: Nowme Zaman | Responsible QA: Nowme Zaman | Responsible QA: Nowme Zaman | Responsible QA: Nowme Zaman | Responsible QA: Nowme Zaman
Bug Reporting | Bug Reporting | Bug Reporting
# SL 17 | # SL 18 | # SL 19
Issue: All mandatory fields missing red asterisk | Issue: 'Click here' link did not resend confirmation mail | Issue: Functionality of 'Login' button not working
Reproducing Steps: | Reproducing Steps: | Reproducing Steps:
1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Check all mandatory fields | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Enter valid credentials to login 4. Click on 'click here' link to get confirmation mail | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button 3. Login with valid credentials
Env: Production | Env: Production | Env: Production
Module: Sign Up | Module: Sign Up | Module: Sign Up
Severity: P1 | Severity: P1 | Severity: P0
Screenshot: Mandatory fields missing red asterisk | Screenshot: resend confirmation mail link not working | Screenshot: Account is not verified
Expected: All mandatory fields should be marked with red asterisk | Expected: Should resend confirmation mail successfully | Expected: Should allow user to login with valid credentials after account verification
Responsible QA: Nowme Zaman | Responsible QA: Nowme Zaman | Responsible QA: Nowme Zaman

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (92/92)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/92)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (73/92)*100 = 79.3%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (19/92)*100 = 20.6%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/92)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A